## SpeciesLists
Domain | Site | Taxon | USU | Initials | Notes | date_in_ops | sp_list_complete_date | priority_for_completing_species_lists
1 | HARV | reptiles | yes | JS | complete to county and state level | 2013-06-01 | 2013-02-06 | 45
1 | HARV | amphibians | yes | JS | complete to county and state level | 2013-06-01 | 2013-02-06 | 46
1 | HARV | small mammals | yes | JS | complete to site level: from Harvard Forest web site | 2013-06-01 | 2013-02-06 | 41
1 | HARV | birds | yes | JS | complete to site level: from Harvard Forest web site | 2013-06-01 | 2013-02-06 | 42
1 | HARV | trees/shrubs | yes | JS | complete to site level: from Harvard Forest web site | 2013-06-01 | 2013-02-06 | 43
1 | HARV | forbs/grasses | yes | JS | complete to site level: from Harvard Forest web site | 2013-06-01 | 2013-02-06 | 44
1 | HARV | mosquitoes | yes | JS | complete to state/regional level | 2013-06-01 | 2013-02-06 | 48
1 | HARV | beetles | yes | JS | complete to state/regional level: email between XX and Erin M. Ellison senior research fellow at Harvard Forest, collection there has not been identified down to the species level but he communicated NEON would be more than welcom to come there and identify them. | 2013-06-01 | 2013-02-06 | 47
1 | BART | birds | yes | JS | complete to site level | 2014-06-01 | 2013-07-31 | 98
1 | BART | trees/shrubs | yes | JS | complete to site level (old 1971)-- email record between KL and John Brisette but it looks like nothing came of it. | 2014-06-01 | 2013-07-31 | 99
1 | BART | beetles | yes | JS | complete to stat level-- UNH insect collection species list | 2014-06-01 | 2013-07-31 | 103
1 | BART | reptiles | yes | JS | complete to state level-- fish and game species list | 2014-06-01 | 2013-07-31 | 101
1 | BART | amphibians | yes | JS | complete to state level-- fish and game species list | 2014-06-01 | 2013-07-31 | 102
1 | BART | small mammals | yes | JS | complete to state level: us fish and game state mammal list | 2014-06-01 | 2013-07-31 | 97
1 | BART | forbs/grasses | yes | JS | incomplete list at site level--EHS veg survey couldn't find another source | 2014-06-01 | 2013-07-31 | 100
1 | BART | mosquitoes | yes | JS | incomplete list to state level--only included species that carry disease | 2014-06-01 | 2013-07-31 | 104
1 | BURL | small mammals | no |  |  | 2015-06-01 |  | 185
1 | BURL | trees/shrubs | no |  |  | 2015-06-01 |  | 187
1 | BURL | reptiles | no |  |  | 2015-06-01 |  | 189
1 | BURL | amphibians | no |  |  | 2015-06-01 |  | 190
1 | BURL | beetles | no |  |  | 2015-06-01 |  | 191
1 | BURL | birds | yes |  | data was for PLUM - not BURL | 2015-06-01 |  | 186
1 | BURL | forbs/grasses | yes |  | data was for PLUM - not BURL | 2015-06-01 |  | 188
1 | BURL | mosquitoes | yes |  | data was for PLUM - not BURL | 2015-06-01 |  | 192
2 | SCBI | small mammals | yes | JS | complete to county level. No list for site level e-mail with William J. Mcshea seems to have indicated that they did not want to expend the effort to dia up data for us | 2014-05-01 | 2013-07-31 | 57
2 | SCBI | reptiles | yes | JS | complete to county level. No list for site level e-mail with William J. Mcshea seems to have indicated that they did not want to expend the effort to dia up data for us | 2014-05-01 | 2013-07-31 | 61
2 | SCBI | amphibians | yes | JS | complete to county level. No list for site level e-mail with William J. Mcshea seems to have indicated that they did not want to expend the effort to dia up data for us | 2014-05-01 | 2013-07-31 | 62
2 | SCBI | trees/shrubs | yes | JS | complete to offsite level | 2014-05-01 | 2013-07-31 | 59
2 | SCBI | forbs/grasses | yes | JS | complete to offsite level | 2014-05-01 | 2013-07-31 | 60
2 | SCBI | beetles | yes | JS | complete to offsite/state level | 2014-05-01 | 2013-07-31 | 63
2 | SCBI | birds | yes | JS | complete to regional level. | 2014-05-01 | 2013-07-31 | 58
2 | SCBI | mosquitoes | yes | JS | complete to state level | 2014-05-01 | 2013-07-31 | 64
2 | SERC | small mammals | yes |  |  | 2014-05-01 | 2013-07-31 | 65
2 | SERC | birds | yes |  |  | 2014-05-01 | 2013-07-31 | 66
2 | SERC | trees/shrubs | yes |  |  | 2014-05-01 | 2013-07-31 | 67
2 | SERC | forbs/grasses | yes |  |  | 2014-05-01 | 2013-07-31 | 68
2 | SERC | reptiles | yes |  |  | 2014-05-01 | 2013-07-31 | 69
2 | SERC | amphibians | yes |  |  | 2014-05-01 | 2013-07-31 | 70
2 | SERC | beetles | yes |  |  | 2014-05-01 | 2013-07-31 | 71
2 | SERC | mosquitoes | yes |  |  | 2014-05-01 | 2013-07-31 | 72
2 | BLAN | amphibians | no | JE | county level from VA Herp Society | 2016-05-01 | 2013-10-18 | 278
2 | BLAN | small mammals | yes |  |  | 2016-05-01 |  | 273
2 | BLAN | birds | yes |  |  | 2016-05-01 |  | 274
2 | BLAN | trees/shrubs | yes |  |  | 2016-05-01 |  | 275
2 | BLAN | forbs/grasses | yes |  |  | 2016-05-01 |  | 276
2 | BLAN | reptiles | yes |  |  | 2016-05-01 |  | 277
2 | BLAN | beetles | yes |  |  | 2016-05-01 |  | 279
2 | BLAN | mosquitoes | yes |  |  | 2016-05-01 |  | 280
3 | DSNY | mosquitoes | yes | JS | complete to county level -- e-mail to mosquito vector from EB but no record of response | 2013-05-01 | 2013-02-06 | 8
3 | DSNY | small mammals | yes | JS | complete to site level | 2013-05-01 | 2013-02-06 | 1
3 | DSNY | birds | yes | JS | complete to site level | 2013-05-01 | 2013-02-06 | 2
3 | DSNY | reptiles | yes | JS | complete to site level | 2013-05-01 | 2013-02-06 | 5
3 | DSNY | amphibians | yes | JS | complete to site level | 2013-05-01 | 2013-02-06 | 6
3 | DSNY | beetles | yes | JS | complete to site level | 2013-05-01 | 2013-02-06 | 7
3 | DSNY | trees/shrubs | yes | JS | complete to site level -- Found e-mail records for ZB to Catherine Bowman <garberia08@gmail.com President, Tarflower Chapter FNPS about disney plant species lists. E-mail indicates that data file was sent to Zack directly from her. Plant list list from DWP contains many creative labels and notes | 2013-05-01 | 2013-02-06 | 3
3 | DSNY | forbs/grasses | yes | JS | complete to site level; Plant list list from DWP contains many creative labels and notes | 2013-05-01 | 2013-02-06 | 4
3 | OSBS | beetles | yes | JS | complete -- Annotated grasshopper...doc in mendeley link leads to Annotated beetle list Doc is title incorrectly in Mendeley and in USU invertebrates species list | 2013-05-01 | 2013-02-06 | 15
3 | OSBS | mosquitoes | yes | JS | complete to county level: Found species distribution of mosquitoes from http://mosquito.ifas.ufl.edu/FMD/Florida_Mosquito_Database.html and created lists of mosquitoes for DSNY and OSBS | 2013-05-01 | 2013-02-06 | 16
3 | OSBS | small mammals | yes | JS | complete to site level | 2013-05-01 | 2013-02-06 | 9
3 | OSBS | birds | yes | JS | complete to site level | 2013-05-01 | 2013-02-06 | 10
3 | OSBS | trees/shrubs | yes | JS | complete to site level | 2013-05-01 | 2013-02-06 | 11
3 | OSBS | forbs/grasses | yes | JS | complete to site level | 2013-05-01 | 2013-02-06 | 12
3 | OSBS | reptiles | yes | JS | complete to site level | 2013-05-01 | 2013-02-06 | 13
3 | OSBS | amphibians | yes | JS | complete to site level | 2013-05-01 | 2013-02-06 | 14
3 | JERC | beetles | yes | JE | complete | 2014-05-01 | 2013-07-31 | 55
3 | JERC | small mammals | yes | JE | complete - no correspondence on file | 2014-05-01 | 2013-07-31 | 49
3 | JERC | birds | yes | JE | complete - no correspondence on file | 2014-05-01 | 2013-07-31 | 50
3 | JERC | reptiles | yes | JE | complete - no correspondence on file | 2014-05-01 | 2013-07-31 | 53
3 | JERC | amphibians | yes | JE | complete - no correspondence on file | 2014-05-01 | 2013-07-31 | 54
3 | JERC | mosquitoes | yes | JE | complete - no correspondence on file; No data on MosquitoMap/VectorServ. | 2014-05-01 | 2013-07-31 | 56
3 | JERC | trees/shrubs | yes | JE | complete - regex confirmation warranted | 2014-05-01 | 2013-07-31 | 51
3 | JERC | forbs/grasses | yes | JE | complete - regex confirmation warranted | 2014-05-01 | 2013-07-31 | 52
4 | GUAN | trees/shrubs | no | JE | list for Antillean dry forest | 2015-03-01 | 2014-04-23 | 123
4 | GUAN | forbs/grasses | no | JE | list for Antillean dry forest | 2015-03-01 | 2014-04-23 | 124
4 | GUAN | beetles | no |  |  | 2015-03-01 |  | 127
4 | GUAN | small mammals | yes |  |  | 2015-03-01 |  | 121
4 | GUAN | birds | yes |  |  | 2015-03-01 |  | 122
4 | GUAN | reptiles | yes |  | MIGHT BE A GOOD RESOURCE - http://prgap.org/datasets/ | 2015-03-01 |  | 125
4 | GUAN | amphibians | yes |  | MIGHT BE A GOOD RESOURCE - http://prgap.org/datasets/ | 2015-03-01 |  | 126
4 | GUAN | mosquitoes | yes |  |  | 2015-03-01 |  | 128
4 | LAJA | small mammals | no |  |  | 2016-03-01 |  | 241
4 | LAJA | birds | no |  |  | 2016-03-01 |  | 242
4 | LAJA | trees/shrubs | no |  |  | 2016-03-01 |  | 243
4 | LAJA | forbs/grasses | no |  |  | 2016-03-01 |  | 244
4 | LAJA | reptiles | no |  | MIGHT BE A GOOD RESOURCE - http://prgap.org/datasets/ | 2016-03-01 |  | 245
4 | LAJA | amphibians | no |  | MIGHT BE A GOOD RESOURCE - http://prgap.org/datasets/ | 2016-03-01 |  | 246
4 | LAJA | beetles | no |  |  | 2016-03-01 |  | 247
4 | MAME | small mammals | no |  |  | 2016-03-01 |  | 249
4 | MAME | birds | no |  |  | 2016-03-01 |  | 250
4 | MAME | trees/shrubs | no |  |  | 2016-03-01 |  | 251
4 | MAME | forbs/grasses | no |  |  | 2016-03-01 |  | 252
4 | MAME | reptiles | no |  | MIGHT BE A GOOD RESOURCE - http://prgap.org/datasets/ | 2016-03-01 |  | 253
4 | MAME | amphibians | no |  | MIGHT BE A GOOD RESOURCE - http://prgap.org/datasets/ | 2016-03-01 |  | 254
4 | MAME | beetles | no |  |  | 2016-03-01 |  | 255
4 | LAJA | mosquitoes | yes |  |  | 2016-03-01 |  | 248
4 | MAME | mosquitoes | yes |  |  | 2016-03-01 |  | 256
5 | UNDE | small mammals | yes | JE | complete to site level (from u of notre dame); email record between ZB and Gary Belovsky | 2014-06-01 | 2013-07-31 | 113
5 | UNDE | birds | yes | JE | complete to site level (from underc-east) and from breeding bird survey; email record between ZB and Gary Belovsky | 2014-06-01 | 2013-07-31 | 114
5 | UNDE | reptiles | yes | JE | complete to site level (underc-east herps list); email record between ZB and Gary Belovsky | 2014-06-01 | 2013-07-31 | 117
5 | UNDE | amphibians | yes | JE | complete to site level (underc-east herps list); email record between ZB and Gary Belovsky | 2014-06-01 | 2013-07-31 | 118
5 | UNDE | trees/shrubs | yes | JE | complete to site level (underc-east plant list and veg list from Copperwood Project); email record between ZB and Gary Belovsky | 2014-06-01 | 2013-07-31 | 115
5 | UNDE | forbs/grasses | yes | JE | complete to site level (underc-east plant list and veg list from Copperwood Project); email record between ZB and Gary Belovsky | 2014-06-01 | 2013-07-31 | 116
5 | UNDE | mosquitoes | yes | JE | complete to state level (mosquitoes of Wisconsin from 1944); email record between ZB and Gary Belovsky, list received from Prof. Hellenthal | 2014-06-01 | 2013-07-31 | 120
5 | UNDE | beetles | yes | JE | site-specific beetle list from ZB's communication with Gary Belovsky | 2014-06-01 | 2013-07-31 | 119
5 | STEI | small mammals | no | JE | WI's Northwoods mammals from Arkive… search for more | 2015-06-01 | 2013-10-04 | 201
5 | STEI | forbs/grasses | no |  | region level - Northwoods plants from ARKive | 2015-06-01 | 2013-10-04 | 204
5 | STEI | reptiles | no |  | WI's Northwoods reptiles from ARKive… search for more specific | 2015-06-01 | 2013-10-04 | 205
5 | STEI | amphibians | no |  | WI's Northwoods amphibians from Arkive… search for more | 2015-06-01 | 2013-10-04 | 206
5 | STEI | beetles | no |  |  | 2015-06-01 |  | 207
5 | TREE | small mammals | no | JE | WI's Northwoods mammals from Arkive… search for more | 2015-06-01 | 2013-10-04 | 209
5 | TREE | reptiles | no | JE | WI's Northwoods reptiles from ARKive… search for more specific | 2015-06-01 | 2013-10-04 | 213
5 | TREE | amphibians | no | JE | WI's Northwoods amphibians from Arkive… search for more | 2015-06-01 | 2013-10-04 | 214
5 | TREE | beetles | no |  |  | 2015-06-01 |  | 215
5 | STEI | birds | yes |  | county level data from Wisconsin breeding bird atlas | 2015-06-01 | 2013-10-04 | 202
5 | STEI | trees/shrubs | yes |  | region level - Northwoods plants from ARKive | 2015-06-01 | 2013-10-04 | 203
5 | STEI | mosquitoes | yes |  |  | 2015-06-01 |  | 208
5 | TREE | birds | yes | JE | county level data from Wisconsin breeding bird atlas | 2015-06-01 | 2013-10-04 | 210
5 | TREE | trees/shrubs | yes | JE | region level - Northwoods plants from ARKive | 2015-06-01 | 2013-10-04 | 211
5 | TREE | forbs/grasses | yes | JE | region level - Northwoods plants from ARKive | 2015-06-01 | 2013-10-04 | 212
5 | TREE | mosquitoes | yes |  |  | 2015-06-01 |  | 216
6 | KONZ | small mammals | no | JE | complete - species list from Konza LTER | 2016-04-01 | 2013-06-12 | 265
6 | KONZ | birds | no | JE | complete - species list from Konza LTER | 2016-04-01 | 2013-06-12 | 266
6 | KONZ | trees/shrubs | no | JE | complete - species list from Konza LTER | 2016-04-01 | 2013-06-12 | 267
6 | KONZ | forbs/grasses | no | JE | complete - species list from Konza LTER | 2016-04-01 | 2013-06-12 | 268
6 | KONZ | reptiles | no | JE | complete - species list from Konza LTER | 2016-04-01 | 2013-06-12 | 269
6 | KONZ | amphibians | no | JE | complete - species list from Konza LTER | 2016-04-01 | 2013-06-12 | 270
6 | KONZ | beetles | no | JE | complete - species list from Konza LTER | 2016-04-01 | 2013-06-12 | 271
6 | KONZ | mosquitoes | yes | JE | in Dodobase from Utah students | 2016-04-01 |  | 272
6 | KONA | small mammals | no | JE | complete - species list from Konza LTER | 2017-04-01 | 2013-06-12 | 425
6 | KONA | birds | no | JE | complete - species list from Konza LTER | 2017-04-01 | 2013-06-12 | 426
6 | KONA | trees/shrubs | no | JE | complete - species list from Konza LTER | 2017-04-01 | 2013-06-12 | 427
6 | KONA | forbs/grasses | no | JE | complete - species list from Konza LTER | 2017-04-01 | 2013-06-12 | 428
6 | KONA | reptiles | no | JE | complete - species list from Konza LTER | 2017-04-01 | 2013-06-12 | 429
6 | KONA | amphibians | no | JE | complete - species list from Konza LTER | 2017-04-01 | 2013-06-12 | 430
6 | KONA | beetles | no | JE | complete - species list from Konza LTER | 2017-04-01 | 2013-06-12 | 431
6 | KUFS | birds | no | JE | complete - KUFS bird checklist | 2017-04-01 | 2013-06-13 | 434
6 | KUFS | reptiles | no | JE | complete - KUFS herps (reptile and amphibians) list | 2017-04-01 | 2013-06-13 | 437
6 | KUFS | amphibians | no | JE | complete - KUFS herps (reptile and amphibians) list | 2017-04-01 | 2013-06-13 | 438
6 | KUFS | small mammals | no | JE | complete - KUFS mammal checklist | 2017-04-01 | 2013-06-13 | 433
6 | KUFS | trees/shrubs | no | JE | complete - KUFS vascular plant list | 2017-04-01 | 2013-06-13 | 435
6 | KUFS | forbs/grasses | no | JE | complete - KUFS vascular plant list | 2017-04-01 | 2013-06-13 | 436
6 | KUFS | beetles | no |  |  | 2017-04-01 |  | 439
6 | KONA | mosquitoes | yes | JE | in Dodobase from Utah students | 2017-04-01 |  | 432
6 | KUFS | mosquitoes | yes |  |  | 2017-04-01 |  | 440
7 | ORNL | small mammals | yes | JE | complete - no email records | 2014-05-01 | 2013-07-31 | 81
7 | ORNL | birds | yes | JE | complete - no email records | 2014-05-01 | 2013-07-31 | 82
7 | ORNL | trees/shrubs | yes | JE | complete - no email records | 2014-05-01 | 2013-07-31 | 83
7 | ORNL | forbs/grasses | yes | JE | complete - no email records | 2014-05-01 | 2013-07-31 | 84
7 | ORNL | reptiles | yes | JE | complete - no email records | 2014-05-01 | 2013-07-31 | 85
7 | ORNL | amphibians | yes | JE | complete - no email records | 2014-05-01 | 2013-07-31 | 86
7 | ORNL | beetles | yes | JE | incomplete - needs work | 2014-05-01 | 2013-07-31 | 87
7 | ORNL | mosquitoes | yes | JE | no data on mosquito map/vector serv - search elsewhere | 2014-05-01 | 2013-07-31 | 88
7 | MLBS | small mammals | yes |  |  | 2015-05-01 |  | 153
7 | MLBS | birds | yes |  |  | 2015-05-01 |  | 154
7 | MLBS | trees/shrubs | yes |  |  | 2015-05-01 |  | 155
7 | MLBS | forbs/grasses | yes |  |  | 2015-05-01 |  | 156
7 | MLBS | reptiles | yes |  |  | 2015-05-01 |  | 157
7 | MLBS | amphibians | yes |  |  | 2015-05-01 |  | 158
7 | MLBS | beetles | yes |  |  | 2015-05-01 |  | 159
7 | MLBS | mosquitoes | yes |  |  | 2015-05-01 |  | 160
7 | GRSM | small mammals | yes |  |  | 2016-05-01 |  | 297
7 | GRSM | birds | yes |  |  | 2016-05-01 |  | 298
7 | GRSM | trees/shrubs | yes |  |  | 2016-05-01 |  | 299
7 | GRSM | forbs/grasses | yes |  |  | 2016-05-01 |  | 300
7 | GRSM | reptiles | yes |  |  | 2016-05-01 |  | 301
7 | GRSM | amphibians | yes |  |  | 2016-05-01 |  | 302
7 | GRSM | beetles | yes |  |  | 2016-05-01 |  | 303
7 | GRSM | mosquitoes | yes |  |  | 2016-05-01 |  | 304
8 | TALL | small mammals | yes | HA | complete-email records found between XX and Tom Haggerty and Eric Sorenson | 2014-05-01 | 2013-07-31 | 73
8 | TALL | birds | yes | HA | complete-email records found between XX and Tom Haggerty and Eric Sorenson | 2014-05-01 | 2013-07-31 | 74
8 | TALL | trees/shrubs | yes | HA | complete-no correspondence on file | 2014-05-01 | 2013-07-31 | 75
8 | TALL | forbs/grasses | yes | HA | complete-no correspondence on file | 2014-05-01 | 2013-07-31 | 76
8 | TALL | reptiles | yes | HA | complete-no correspondence on file | 2014-05-01 | 2013-07-31 | 77
8 | TALL | amphibians | yes | HA | complete-no correspondence on file | 2014-05-01 | 2013-07-31 | 78
8 | TALL | beetles | yes | HA |  | 2014-05-01 | 2013-07-31 | 79
8 | TALL | mosquitoes | yes | HA |  | 2014-05-01 | 2013-07-31 | 80
8 | DELA | small mammals | no |  | regional Smithsonian info | 2015-05-01 |  | 137
8 | DELA | trees/shrubs | no |  |  | 2015-05-01 |  | 139
8 | DELA | forbs/grasses | no |  |  | 2015-05-01 |  | 140
8 | DELA | amphibians | no |  |  | 2015-05-01 |  | 142
8 | DELA | beetles | no |  |  | 2015-05-01 |  | 143
8 | DELA | birds | yes |  |  | 2015-05-01 |  | 138
8 | DELA | reptiles | yes |  |  | 2015-05-01 |  | 141
8 | DELA | mosquitoes | yes |  |  | 2015-05-01 |  | 144
8 | CHOC | small mammals | no |  |  | 2016-05-01 |  | 281
8 | CHOC | reptiles | no |  |  | 2016-05-01 |  | 285
8 | CHOC | amphibians | no |  |  | 2016-05-01 |  | 286
8 | CHOC | beetles | no |  |  | 2016-05-01 |  | 287
8 | CHOC | birds | yes |  |  | 2016-05-01 |  | 282
8 | CHOC | trees/shrubs | yes |  |  | 2016-05-01 |  | 283
8 | CHOC | forbs/grasses | yes |  |  | 2016-05-01 |  | 284
8 | CHOC | mosquitoes | yes |  |  | 2016-05-01 |  | 288
9 | WOOD | beetles | yes | JS | complete to offsite level (within same county) | 2014-06-01 | 2013-07-31 | 111
9 | WOOD | mosquitoes | yes | JS | complete to offsite level (within same county)--however could use more work | 2014-06-01 | 2013-07-31 | 112
9 | WOOD | small mammals | yes | JS | complete to site and regional level--USGS data portal (Northern Prairie Wildlife Research Center) | 2014-06-01 | 2013-07-31 | 105
9 | WOOD | birds | yes | JS | complete to site level--USGS data portal (Northern Prairie Wildlife Research Center) | 2014-06-01 | 2013-07-31 | 106
9 | WOOD | trees/shrubs | yes | JS | complete to site level--USGS data portal (Northern Prairie Wildlife Research Center) | 2014-06-01 | 2013-07-31 | 107
9 | WOOD | forbs/grasses | yes | JS | complete to site level--USGS data portal (Northern Prairie Wildlife Research Center) | 2014-06-01 | 2013-07-31 | 108
9 | WOOD | reptiles | yes | JS | complete to site level--USGS data portal (Northern Prairie Wildlife Research Center) | 2014-06-01 | 2013-07-31 | 109
9 | WOOD | amphibians | yes | JS | complete to site level--USGS data portal (Northern Prairie Wildlife Research Center) | 2014-06-01 | 2013-07-31 | 110
9 | DCFS | small mammals | yes |  | complete but mostly duplicated from WOOD lists | 2015-05-01 |  | 129
9 | DCFS | birds | yes |  | complete but mostly duplicated from WOOD lists | 2015-05-01 |  | 130
9 | DCFS | trees/shrubs | yes |  | complete but mostly duplicated from WOOD lists | 2015-05-01 |  | 131
9 | DCFS | forbs/grasses | yes |  | complete but mostly duplicated from WOOD lists | 2015-05-01 |  | 132
9 | DCFS | reptiles | yes |  | complete but mostly duplicated from WOOD lists | 2015-05-01 |  | 133
9 | DCFS | amphibians | yes |  | complete but mostly duplicated from WOOD lists | 2015-05-01 |  | 134
9 | DCFS | beetles | yes |  | north dakota (state level info) | 2015-05-01 |  | 135
9 | DCFS | mosquitoes | yes |  | state level vector map | 2015-05-01 |  | 136
9 | NOGP | beetles | no |  |  | 2015-06-01 |  | 199
9 | NOGP | small mammals | yes |  | Knife River Indian Villages -- more of a regional source | 2015-06-01 |  | 193
9 | NOGP | birds | yes |  |  | 2015-06-01 |  | 194
9 | NOGP | trees/shrubs | yes |  |  | 2015-06-01 |  | 195
9 | NOGP | forbs/grasses | yes |  |  | 2015-06-01 |  | 196
9 | NOGP | reptiles | yes |  | Knife River Indian Villages -- more of a regional source | 2015-06-01 |  | 197
9 | NOGP | amphibians | yes |  | Knife River Indian Villages -- more of a regional source | 2015-06-01 |  | 198
9 | NOGP | mosquitoes | yes |  |  | 2015-06-01 |  | 200
10 | CPER | small mammals | yes | JE | complete but no emails found | 2013-05-01 | 2013-02-06 | 17
10 | CPER | birds | yes | JE | complete but no emails found | 2013-05-01 | 2013-02-06 | 18
10 | CPER | trees/shrubs | yes | JE | complete but no emails found | 2013-05-01 | 2013-02-06 | 19
10 | CPER | forbs/grasses | yes | JE | complete but no emails found | 2013-05-01 | 2013-02-06 | 20
10 | CPER | reptiles | yes | JE | complete but no emails found | 2013-05-01 | 2013-02-06 | 21
10 | CPER | amphibians | yes | JE | complete but no emails found | 2013-05-01 | 2013-02-06 | 22
10 | CPER | beetles | yes | JE | complete but no emails found | 2013-05-01 | 2013-02-06 | 23
10 | CPER | mosquitoes | yes | JE | complete; found emails between Ken Locey and Boris C. Kondratieff | 2013-05-01 | 2013-02-06 | 24
10 | STER | small mammals | yes | JE | complete; found emails between Zack Brym and Jeff Thompson (STER) | 2013-05-01 | 2013-02-06 | 25
10 | STER | birds | yes | JE | complete; found emails between Zack Brym and Jeff Thompson (STER) | 2013-05-01 | 2013-02-06 | 26
10 | STER | reptiles | yes | JE | complete; found emails between Zack Brym and Jeff Thompson (STER) | 2013-05-01 | 2013-02-06 | 29
10 | STER | amphibians | yes | JE | complete; found emails between Zack Brym and Jeff Thompson (STER) | 2013-05-01 | 2013-02-06 | 30
10 | STER | trees/shrubs | yes | JE | complete; found emails between Zack Brym and Jeff Thompson (STER) 6/29/12 | 2013-05-01 | 2013-02-06 | 27
10 | STER | forbs/grasses | yes | JE | complete; found emails between Zack Brym and Jeff Thompson (STER) 6/29/12 | 2013-05-01 | 2013-02-06 | 28
10 | STER | beetles | yes | JE | county level - incomplete | 2013-05-01 | 2013-02-06 | 31
10 | STER | mosquitoes | yes | JE | no data on mosquito map/vectorserv. | 2013-05-01 | 2013-02-06 | 32
10 | RMNP | small mammals | yes | JS | complete to site level: came from IRMA data portal | 2013-06-01 | 2013-02-06 | 33
10 | RMNP | birds | yes | JS | complete to site level: came from IRMA data portal | 2013-06-01 | 2013-02-06 | 34
10 | RMNP | trees/shrubs | yes | JS | complete to site level: came from IRMA data portal | 2013-06-01 | 2013-02-06 | 35
10 | RMNP | forbs/grasses | yes | JS | complete to site level: came from IRMA data portal | 2013-06-01 | 2013-02-06 | 36
10 | RMNP | reptiles | yes | JS | complete to site level: came from IRMA data portal | 2013-06-01 | 2013-02-06 | 37
10 | RMNP | amphibians | yes | JS | complete to site level: came from IRMA data portal | 2013-06-01 | 2013-02-06 | 38
10 | RMNP | beetles | yes | JS | Not sure what the source is | 2013-06-01 | 2013-02-06 | 39
10 | RMNP | mosquitoes | yes | JS | Not sure what the source is | 2013-06-01 | 2013-02-06 | 40
11 | OAES | small mammals | no |  |  | 2015-05-01 |  | 169
11 | OAES | birds | no |  |  | 2015-05-01 |  | 170
11 | OAES | trees/shrubs | no |  |  | 2015-05-01 |  | 171
11 | OAES | forbs/grasses | no |  |  | 2015-05-01 |  | 172
11 | OAES | reptiles | no | JE | county level list | 2015-05-01 | 2014-01-28 | 173
11 | OAES | amphibians | no | JE | county level list | 2015-05-01 | 2014-01-28 | 174
11 | OAES | beetles | no |  |  | 2015-05-01 |  | 175
11 | OAES | mosquitoes | yes |  |  | 2015-05-01 |  | 176
11 | CLBJ | small mammals | no |  |  | 2016-05-01 |  | 313
11 | CLBJ | birds | no |  |  | 2016-05-01 |  | 314
11 | CLBJ | trees/shrubs | no |  |  | 2016-05-01 |  | 315
11 | CLBJ | forbs/grasses | no |  |  | 2016-05-01 |  | 316
11 | CLBJ | reptiles | no | JE | county list from 1970s masters thesis | 2016-05-01 |  | 317
11 | CLBJ | amphibians | no | JE | county list from 1970s masters thesis | 2016-05-01 |  | 318
11 | CLBJ | beetles | no |  |  | 2016-05-01 |  | 319
11 | CLBJ | mosquitoes | yes |  |  | 2016-05-01 |  | 320
11 | tbd | small mammals | no |  |  | 2016-06-01 |  | 337
11 | tbd | birds | no |  |  | 2016-06-01 |  | 338
11 | tbd | trees/shrubs | no |  |  | 2016-06-01 |  | 339
11 | tbd | forbs/grasses | no |  |  | 2016-06-01 |  | 340
11 | tbd | reptiles | no |  |  | 2016-06-01 |  | 341
11 | tbd | amphibians | no |  |  | 2016-06-01 |  | 342
11 | tbd | beetles | no |  |  | 2016-06-01 |  | 343
11 | tbd | mosquitoes | yes |  |  | 2016-06-01 |  | 344
12 | YELL | amphibians | no | JE | complete (YELL amphibians certified sp list from NPS) | 2016-06-01 | 2013-07-29 | 350
12 | YELL | small mammals | no | JE | complete (YELL certified sp list from NPS) | 2016-06-01 | 2013-07-29 | 345
12 | YELL | birds | no | JE | complete (YELL certified sp list from NPS) | 2016-06-01 | 2013-07-29 | 346
12 | YELL | trees/shrubs | no | JE | complete (YELL certifield vascular plant list from NPS) | 2016-06-01 | 2013-07-29 | 347
12 | YELL | forbs/grasses | no | JE | complete (YELL certifield vascular plant list from NPS) | 2016-06-01 | 2013-07-29 | 348
12 | YELL | reptiles | no | JE | complete (YELL reptile certified sp list from NPS) | 2016-06-01 | 2013-07-29 | 349
12 | YELL | beetles | no |  | found list from Yellowstone Wiki - emailed Yellowstone Center for Resources to check on validity | 2016-06-01 |  | 351
12 | YELL | mosquitoes | yes |  |  | 2016-06-01 |  | 352
12 | BOZE | small mammals | no | JE | complete (BOZE specific info from Montana Natural Heritage Map Viewer) | 2017-03-01 | 2013-07-30 | 377
12 | BOZE | birds | no | JE | complete (BOZE specific info from Montana Natural Heritage Map Viewer) | 2017-03-01 | 2013-07-30 | 378
12 | BOZE | trees/shrubs | no | JE | complete (city of BOZE tree guide; south-central MT native plant society list) | 2017-03-01 | 2013-07-30 | 379
12 | BOZE | forbs/grasses | no |  | south-central MT native plant society list | 2017-03-01 |  | 380
12 | BOZE | reptiles | no | JE | complete (BOZE specific info from Montana Natural Heritage Map Viewer) | 2017-03-01 | 2013-07-30 | 381
12 | BOZE | amphibians | no | JE | complete (BOZE specific info from Montana Natural Heritage Map Viewer) | 2017-03-01 | 2013-07-30 | 382
12 | BOZE | beetles | no | JE | complete (BOZE specific info from Montana Natural Heritage Map Viewer) | 2017-03-01 | 2013-07-30 | 383
12 | BOZE | mosquitoes | yes |  |  | 2017-03-01 |  | 384
12 | PARA | small mammals | no | JE | complete (PARA specific info from Montana Natural Heritage Map Viewer) | 2017-06-01 | 2013-07-30 | 465
12 | PARA | birds | no | JE | complete (PARA specific info from Montana Natural Heritage Map Viewer) | 2017-06-01 | 2013-07-30 | 466
12 | PARA | trees/shrubs | no |  |  | 2017-06-01 |  | 467
12 | PARA | forbs/grasses | no |  |  | 2017-06-01 |  | 468
12 | PARA | reptiles | no | JE | complete (PARA specific info from Montana Natural Heritage Map Viewer) | 2017-06-01 | 2013-07-30 | 469
12 | PARA | amphibians | no | JE | complete (PARA specific info from Montana Natural Heritage Map Viewer) | 2017-06-01 | 2013-07-30 | 470
12 | PARA | beetles | no | JE | complete (PARA specific info from Montana Natural Heritage Map Viewer) | 2017-06-01 | 2013-07-30 | 471
12 | PARA | mosquitoes | yes |  |  | 2017-06-01 |  | 472
13 | MOAB | small mammals | yes |  |  | 2015-05-01 |  | 161
13 | MOAB | birds | yes |  |  | 2015-05-01 |  | 162
13 | MOAB | trees/shrubs | yes |  |  | 2015-05-01 |  | 163
13 | MOAB | forbs/grasses | yes |  |  | 2015-05-01 |  | 164
13 | MOAB | reptiles | yes |  |  | 2015-05-01 |  | 165
13 | MOAB | amphibians | yes |  |  | 2015-05-01 |  | 166
13 | MOAB | beetles | yes |  |  | 2015-05-01 |  | 167
13 | MOAB | mosquitoes | yes |  |  | 2015-05-01 |  | 168
13 | NIWO | beetles | no |  |  | 2015-06-01 |  | 223
13 | NIWO | small mammals | yes |  |  | 2015-06-01 |  | 217
13 | NIWO | birds | yes |  |  | 2015-06-01 |  | 218
13 | NIWO | trees/shrubs | yes |  |  | 2015-06-01 |  | 219
13 | NIWO | forbs/grasses | yes |  |  | 2015-06-01 |  | 220
13 | NIWO | reptiles | yes |  |  | 2015-06-01 |  | 221
13 | NIWO | amphibians | yes |  |  | 2015-06-01 |  | 222
13 | NIWO | mosquitoes | yes |  |  | 2015-06-01 |  | 224
13 | tbd | small mammals | yes |  |  | 2017-06-01 |  | 457
13 | tbd | birds | yes |  |  | 2017-06-01 |  | 458
13 | tbd | trees/shrubs | yes |  |  | 2017-06-01 |  | 459
13 | tbd | forbs/grasses | yes |  |  | 2017-06-01 |  | 460
13 | tbd | reptiles | yes |  |  | 2017-06-01 |  | 461
13 | tbd | amphibians | yes |  |  | 2017-06-01 |  | 462
13 | tbd | beetles | yes |  |  | 2017-06-01 |  | 463
13 | tbd | mosquitoes | yes |  |  | 2017-06-01 |  | 464
14 | SRER | small mammals | yes |  |  | 2015-05-01 |  | 145
14 | SRER | birds | yes |  |  | 2015-05-01 |  | 146
14 | SRER | trees/shrubs | yes |  |  | 2015-05-01 |  | 147
14 | SRER | forbs/grasses | yes |  |  | 2015-05-01 |  | 148
14 | SRER | reptiles | yes |  |  | 2015-05-01 |  | 149
14 | SRER | amphibians | yes |  |  | 2015-05-01 |  | 150
14 | SRER | beetles | yes |  |  | 2015-05-01 |  | 151
14 | SRER | mosquitoes | yes |  |  | 2015-05-01 |  | 152
14 | JORN | small mammals | yes |  |  | 2016-05-01 |  | 289
14 | JORN | birds | yes |  |  | 2016-05-01 |  | 290
14 | JORN | trees/shrubs | yes |  |  | 2016-05-01 |  | 291
14 | JORN | forbs/grasses | yes |  |  | 2016-05-01 |  | 292
14 | JORN | reptiles | yes |  |  | 2016-05-01 |  | 293
14 | JORN | amphibians | yes |  |  | 2016-05-01 |  | 294
14 | JORN | beetles | yes |  |  | 2016-05-01 |  | 295
14 | JORN | mosquitoes | yes |  |  | 2016-05-01 |  | 296
14 | tbd | small mammals | yes |  |  | 2017-05-01 |  | 441
14 | tbd | birds | yes |  |  | 2017-05-01 |  | 442
14 | tbd | trees/shrubs | yes |  |  | 2017-05-01 |  | 443
14 | tbd | forbs/grasses | yes |  |  | 2017-05-01 |  | 444
14 | tbd | reptiles | yes |  |  | 2017-05-01 |  | 445
14 | tbd | amphibians | yes |  |  | 2017-05-01 |  | 446
14 | tbd | beetles | yes |  |  | 2017-05-01 |  | 447
14 | tbd | mosquitoes | yes |  |  | 2017-05-01 |  | 448
15 | ONAQ | beetles | no | JS | searched and can't find a relevant source | 2014-05-01 | 2013-07-31 | 95
15 | ONAQ | small mammals | yes | JS | complete to county level--from Utah division of wildlife | 2014-05-01 | 2013-07-31 | 89
15 | ONAQ | reptiles | yes | JS | complete to county level--from Utah division of wildlife | 2014-05-01 | 2013-07-31 | 93
15 | ONAQ | amphibians | yes | JS | complete to county level--from Utah division of wildlife | 2014-05-01 | 2013-07-31 | 94
15 | ONAQ | trees/shrubs | yes | JS | complete to site level - email records between Zack Brym and Eugene Shupp, Mark Brunson, James McIver. Response for data request seemed positive but not sure what came of it, e-mail chain ends after Zack sent shapefile of site boundary. | 2014-05-01 | 2013-07-31 | 91
15 | ONAQ | forbs/grasses | yes | JS | complete to site level - email records between Zack Brym and Eugene Shupp, Mark Brunson, James McIver. Response for data request seemed positive but not sure what came of it, e-mail chain ends after Zack sent shapefile of site boundary. | 2014-05-01 | 2013-07-31 | 92
15 | ONAQ | birds | yes | JS | complete to site level- email records between Zack Brym and Eugene Shupp, Mark Brunson, James McIver. Response for data request seemed positive but not sure what came of it, e-mail chain ends after Zack sent shapefile of site boundary. | 2014-05-01 | 2013-07-31 | 90
15 | ONAQ | mosquitoes | yes | JS | complete to state level: usu source not in mendeley, however a few entries in the database.email records between Zack Brym and Eugene Shupp, Mark Brunson, James McIver. Response for data request seemed positive but not sure what came of it, e-mail chain ends after Zack sent shapefile of site boundary. | 2014-05-01 | 2013-07-31 | 96
15 | RBUT | reptiles | no |  |  | 2016-05-01 |  | 309
15 | RBUT | amphibians | no |  |  | 2016-05-01 |  | 310
15 | RBUT | beetles | no |  |  | 2016-05-01 |  | 311
15 | RBUT | small mammals | yes |  |  | 2016-05-01 |  | 305
15 | RBUT | birds | yes |  |  | 2016-05-01 |  | 306
15 | RBUT | trees/shrubs | yes |  |  | 2016-05-01 |  | 307
15 | RBUT | forbs/grasses | yes |  |  | 2016-05-01 |  | 308
15 | RBUT | mosquitoes | yes |  |  | 2016-05-01 |  | 312
15 | tbd | small mammals | no |  |  | 2017-04-01 |  | 401
15 | tbd | birds | no |  |  | 2017-04-01 |  | 402
15 | tbd | trees/shrubs | no |  |  | 2017-04-01 |  | 403
15 | tbd | forbs/grasses | no |  |  | 2017-04-01 |  | 404
15 | tbd | reptiles | no |  |  | 2017-04-01 |  | 405
15 | tbd | amphibians | no |  |  | 2017-04-01 |  | 406
15 | tbd | beetles | no |  |  | 2017-04-01 |  | 407
15 | tbd | mosquitoes | yes |  |  | 2017-04-01 |  | 408
16 | WREF | small mammals | no | JE | some info - small mammal communities of southern cascade mountain range in WA | 2016-05-01 |  | 321
16 | WREF | birds | no | JE | site specific small bird info and nearby songbird list - need more info | 2016-05-01 |  | 322
16 | WREF | trees/shrubs | no | JE | site specific list | 2016-05-01 | 2013-09-26 | 323
16 | WREF | forbs/grasses | no | JE | site specific list | 2016-05-01 | 2013-09-26 | 324
16 | WREF | reptiles | no | JE | site specific list - NEED MORE | 2016-05-01 |  | 325
16 | WREF | amphibians | no | JE | site specific list - NEED MORE | 2016-05-01 |  | 326
16 | WREF | beetles | no | JE | ground beetle list for HJ Andrews Experimental Forest - similar habitat | 2016-05-01 |  | 327
16 | WREF | mosquitoes | yes |  |  | 2016-05-01 |  | 328
16 | ABBY | small mammals | no |  |  | 2017-04-01 |  | 409
16 | ABBY | birds | no |  |  | 2017-04-01 |  | 410
16 | ABBY | trees/shrubs | no |  |  | 2017-04-01 |  | 411
16 | ABBY | forbs/grasses | no |  |  | 2017-04-01 |  | 412
16 | ABBY | reptiles | no |  |  | 2017-04-01 |  | 413
16 | ABBY | amphibians | no |  |  | 2017-04-01 |  | 414
16 | ABBY | beetles | no |  |  | 2017-04-01 |  | 415
16 | THAY | small mammals | no |  |  | 2017-04-01 |  | 417
16 | THAY | birds | no |  |  | 2017-04-01 |  | 418
16 | THAY | trees/shrubs | no |  |  | 2017-04-01 |  | 419
16 | THAY | forbs/grasses | no |  |  | 2017-04-01 |  | 420
16 | THAY | reptiles | no |  |  | 2017-04-01 |  | 421
16 | THAY | amphibians | no |  |  | 2017-04-01 |  | 422
16 | THAY | beetles | no |  |  | 2017-04-01 |  | 423
16 | ABBY | mosquitoes | yes |  |  | 2017-04-01 |  | 416
16 | THAY | mosquitoes | yes |  |  | 2017-04-01 |  | 424
17 | PSRS | trees/shrubs | no | JE | complete - plant checklist for san joaquin experimental range | 2015-05-01 |  | 179
17 | PSRS | forbs/grasses | no | JE | complete - plant checklist for san joaquin experimental range | 2015-05-01 |  | 180
17 | PSRS | small mammals | no | JE | COMPLETE - vertebrate fauna list from USFS for San Joaquin Experimental Range -- site specific | 2015-05-01 | 2013-04-02 | 177
17 | PSRS | birds | no | JE | COMPLETE - vertebrate fauna list from USFS for San Joaquin Experimental Range -- site specific | 2015-05-01 | 2013-04-02 | 178
17 | PSRS | reptiles | no | JE | COMPLETE - vertebrate fauna list from USFS for San Joaquin Experimental Range -- site specific | 2015-05-01 | 2013-04-02 | 181
17 | PSRS | amphibians | no | JE | COMPLETE - vertebrate fauna list from USFS for San Joaquin Experimental Range -- site specific | 2015-05-01 | 2013-04-02 | 182
17 | PSRS | beetles | no |  |  | 2015-05-01 |  | 183
17 | PSRS | mosquitoes | yes |  |  | 2015-05-01 |  | 184
17 | SOAP | small mammals | no |  |  | 2016-05-01 |  | 329
17 | SOAP | birds | no |  |  | 2016-05-01 |  | 330
17 | SOAP | trees/shrubs | no |  |  | 2016-05-01 |  | 331
17 | SOAP | forbs/grasses | no |  |  | 2016-05-01 |  | 332
17 | SOAP | reptiles | no |  |  | 2016-05-01 |  | 333
17 | SOAP | amphibians | no |  |  | 2016-05-01 |  | 334
17 | SOAP | beetles | no |  |  | 2016-05-01 |  | 335
17 | SOAP | mosquitoes | yes |  |  | 2016-05-01 |  | 336
17 | TEAK | trees/shrubs | no | JE | found Teakettle Exp Forest plant list | 2017-05-01 |  | 451
17 | TEAK | forbs/grasses | no | JE | found Teakettle Exp Forest plant list | 2017-05-01 |  | 452
17 | TEAK | small mammals | no |  |  | 2017-05-01 |  | 449
17 | TEAK | birds | no |  |  | 2017-05-01 |  | 450
17 | TEAK | reptiles | no |  |  | 2017-05-01 |  | 453
17 | TEAK | amphibians | no |  |  | 2017-05-01 |  | 454
17 | TEAK | beetles | no |  |  | 2017-05-01 |  | 455
17 | TEAK | mosquitoes | yes |  |  | 2017-05-01 |  | 456
18 | TOOL | small mammals | no | JE | sp list for Gates of the Arctic National Park | 2016-07-01 | 2014-01-27 | 369
18 | TOOL | birds | no |  |  | 2016-07-01 |  | 370
18 | TOOL | trees/shrubs | no |  |  | 2016-07-01 |  | 371
18 | TOOL | forbs/grasses | no |  |  | 2016-07-01 |  | 372
18 | TOOL | reptiles | no | JE | none reported - sp list for Gates of the Arctic National Park | 2016-07-01 | 2014-01-27 | 373
18 | TOOL | amphibians | no | JE | sp list for Gates of the Arctic National Park | 2016-07-01 | 2014-01-27 | 374
18 | TOOL | beetles | no |  |  | 2016-07-01 |  | 375
18 | TOOL | mosquitoes | yes |  |  | 2016-07-01 |  | 376
18 | BARO | small mammals | no |  |  | 2017-07-01 |  | 473
18 | BARO | birds | no |  |  | 2017-07-01 |  | 474
18 | BARO | trees/shrubs | no |  |  | 2017-07-01 |  | 475
18 | BARO | forbs/grasses | no |  |  | 2017-07-01 |  | 476
18 | BARO | reptiles | no | JE | no herps present at site - http://www.scannet.nu/content/view/136/166/ | 2017-07-01 | 2014-01-27 | 477
18 | BARO | amphibians | no | JE | no herps present at site - http://www.scannet.nu/content/view/136/166/ | 2017-07-01 | 2014-01-27 | 478
18 | BARO | beetles | no |  |  | 2017-07-01 |  | 479
18 | BARO | mosquitoes | yes |  |  | 2017-07-01 |  | 480
19 | BONA | small mammals | yes |  | some info | 2015-07-01 |  | 225
19 | BONA | birds | yes |  | some info | 2015-07-01 |  | 226
19 | BONA | forbs/grasses | yes |  | some info | 2015-07-01 |  | 228
19 | BONA | reptiles | yes |  | some info | 2015-07-01 |  | 229
19 | BONA | amphibians | yes |  | some info | 2015-07-01 |  | 230
19 | BONA | beetles | yes |  | some info | 2015-07-01 |  | 231
19 | BONA | mosquitoes | yes |  | some info | 2015-07-01 |  | 232
19 | BONA | trees/shrubs | yes |  |  | 2015-07-01 |  | 227
19 | POKE | small mammals | yes |  | some info | 2015-07-01 |  | 233
19 | POKE | birds | yes |  | some info | 2015-07-01 |  | 234
19 | POKE | forbs/grasses | yes |  | some info | 2015-07-01 |  | 236
19 | POKE | reptiles | yes |  | some info | 2015-07-01 |  | 237
19 | POKE | amphibians | yes |  | some info | 2015-07-01 |  | 238
19 | POKE | beetles | yes |  | some info | 2015-07-01 |  | 239
19 | POKE | mosquitoes | yes |  | some info | 2015-07-01 |  | 240
19 | POKE | trees/shrubs | yes |  |  | 2015-07-01 |  | 235
19 | DEJU | small mammals | no |  |  | 2016-07-01 |  | 353
19 | DEJU | trees/shrubs | no |  |  | 2016-07-01 |  | 355
19 | DEJU | reptiles | no |  |  | 2016-07-01 |  | 357
19 | DEJU | amphibians | no |  |  | 2016-07-01 |  | 358
19 | DEJU | beetles | no |  |  | 2016-07-01 |  | 359
19 | DEJU | birds | yes |  |  | 2016-07-01 |  | 354
19 | DEJU | forbs/grasses | yes |  |  | 2016-07-01 |  | 356
19 | DEJU | mosquitoes | yes |  |  | 2016-07-01 |  | 360
19 | HEAL | small mammals | yes |  | some info | 2016-07-01 |  | 361
19 | HEAL | birds | yes |  | some info | 2016-07-01 |  | 362
19 | HEAL | reptiles | yes |  | some info | 2016-07-01 |  | 365
19 | HEAL | amphibians | yes |  | some info | 2016-07-01 |  | 366
19 | HEAL | beetles | yes |  | some info | 2016-07-01 |  | 367
19 | HEAL | mosquitoes | yes |  | some info | 2016-07-01 |  | 368
19 | HEAL | trees/shrubs | yes |  | very complete vascular plant list | 2016-07-01 |  | 363
19 | HEAL | forbs/grasses | yes |  | very complete vascular plant list | 2016-07-01 |  | 364
20 | OLAA | small mammals | no |  |  | 2016-04-01 |  | 257
20 | OLAA | birds | no |  |  | 2016-04-01 |  | 258
20 | OLAA | trees/shrubs | no |  |  | 2016-04-01 |  | 259
20 | OLAA | forbs/grasses | no |  |  | 2016-04-01 |  | 260
20 | OLAA | reptiles | no |  |  | 2016-04-01 |  | 261
20 | OLAA | amphibians | no |  |  | 2016-04-01 |  | 262
20 | OLAA | beetles | no |  |  | 2016-04-01 |  | 263
20 | OLAA | mosquitoes | yes |  |  | 2016-04-01 |  | 264
20 | PUFO | small mammals | no | JE | site specific list | 2017-03-01 | 2014-01-28 | 385
20 | PUFO | birds | no |  | need to convert from PDF to csv and add to github - IN ZOTERO | 2017-03-01 |  | 386
20 | PUFO | trees/shrubs | no |  | need to convert from PDF to csv and add to github - IN ZOTERO | 2017-03-01 |  | 387
20 | PUFO | forbs/grasses | no |  | need to convert from PDF to csv and add to github - IN ZOTERO | 2017-03-01 |  | 388
20 | PUFO | reptiles | no |  |  | 2017-03-01 |  | 389
20 | PUFO | amphibians | no |  |  | 2017-03-01 |  | 390
20 | PUFO | beetles | no |  | need to convert from PDF to csv and add to github - IN ZOTERO | 2017-03-01 |  | 391
20 | PUGR | small mammals | no |  |  | 2017-03-01 |  | 393
20 | PUGR | birds | no |  |  | 2017-03-01 |  | 394
20 | PUGR | trees/shrubs | no |  |  | 2017-03-01 |  | 395
20 | PUGR | forbs/grasses | no |  |  | 2017-03-01 |  | 396
20 | PUGR | reptiles | no |  |  | 2017-03-01 |  | 397
20 | PUGR | amphibians | no |  |  | 2017-03-01 |  | 398
20 | PUGR | beetles | no |  |  | 2017-03-01 |  | 399
20 | PUFO | mosquitoes | yes |  | need to convert from PDF to csv and add to github - IN ZOTERO | 2017-03-01 |  | 392
20 | PUGR | mosquitoes | yes |  |  | 2017-03-01 |  | 400
Note on B258: Jennifer Everhart: NO NAME YET
Note on B259: Jennifer Everhart: NO NAME YET
Note on B260: Jennifer Everhart: NO NAME YET
Note on B261: Jennifer Everhart: NO NAME YET
Note on B262: Jennifer Everhart: NO NAME YET
Note on B263: Jennifer Everhart: NO NAME YET
Note on B264: Jennifer Everhart: NO NAME YET
Note on B265: Jennifer Everhart: NO NAME YET
Note on B306: Jennifer Everhart: SITE SELECTION ONGOING
Note on B307: Jennifer Everhart: SITE SELECTION ONGOING
Note on B308: Jennifer Everhart: SITE SELECTION ONGOING
Note on B309: Jennifer Everhart: SITE SELECTION ONGOING
Note on B310: Jennifer Everhart: SITE SELECTION ONGOING
Note on B311: Jennifer Everhart: SITE SELECTION ONGOING
Note on B312: Jennifer Everhart: SITE SELECTION ONGOING
Note on B313: Jennifer Everhart: SITE SELECTION ONGOING
Note on B330: Jennifer Everhart: NO NAME YET
Note on B331: Jennifer Everhart: NO NAME YET
Note on B332: Jennifer Everhart: NO NAME YET
Note on B333: Jennifer Everhart: NO NAME YET
Note on B334: Jennifer Everhart: NO NAME YET
Note on B335: Jennifer Everhart: NO NAME YET
Note on B336: Jennifer Everhart: NO NAME YET
Note on B337: Jennifer Everhart: NO NAME YET
Note on B354: Jennifer Everhart: NO NAME YET
Note on B355: Jennifer Everhart: NO NAME YET
Note on B356: Jennifer Everhart: NO NAME YET
Note on B357: Jennifer Everhart: NO NAME YET
Note on B358: Jennifer Everhart: NO NAME YET
Note on B359: Jennifer Everhart: NO NAME YET
Note on B360: Jennifer Everhart: NO NAME YET
Note on B361: Jennifer Everhart: NO NAME YET